## Cover
Azure ML Workbench for R&D Low Level Design Document |  | Flora Food Global Principal B.V. Rackspace Technology ¦ v1.0 ¦ 26 Jun 2026
Document | Flora_AzureML_LowLevel_Design.xlsx
Version | v1.0
Date | 26 June 2026
Prepared By | Rackspace Technology - Azure Cloud Architecture Team
Classification | CONFIDENTIAL
SOW Reference | Account #5760629 / Opportunity #4626144
Workbook Contents
Sheet | Description
Cover | This sheet - document index
Resources | Complete Azure resource inventory with naming, SKU, and config
Network | VNet, subnet, NSG, private endpoint and DNS configuration
Security | RBAC assignments, Key Vault, firewall rules, policies
Compute | Compute Instance and cluster detailed specs
Storage | Storage accounts, datastores, lifecycle policies
MLOps | CI/CD pipeline design, ADO project, environment config
Monitoring | Log Analytics, App Insights, alerts, workbook definitions
Naming | Naming convention standards for all resource types
Milestones | Delivery milestones, acceptance criteria, RACI
Risks | Risk register with likelihood, impact and mitigation
Cost Estimate | Indicative monthly cost estimate per component

## Resources
# | Resource Type | Resource Name | SKU / Tier | Region | Resource Group | Subscription | Environment | Purpose | Dependencies | Configuration Notes
1 | Azure ML Workspace | aml-rd-<env> | Basic | <region> | rg-aml-rd-<env> | <sub-id> | prod/stg/dev | Core ML workspace | Storage, KV, ACR, App Insights | Public access: Disabled. Managed VNet: Enabled. Isolation: Allow approved outbound.
2 | Azure Storage (default) | st-aml-default-<env> | Standard_LRS | <region> | rg-aml-rd-<env> | <sub-id> | prod/stg/dev | Workspace default storage | AML Workspace | Public access: Disabled. HTTPS only. Soft delete: 14 days. Hierarchical namespace: Enabled.
3 | Azure Storage (data) | st-aml-data-<env> | Standard_LRS | <region> | rg-aml-rd-<env> | <sub-id> | prod/stg/dev | R&D dataset storage | AML Workspace | Public access: Disabled. Lifecycle: archive >90 days.
4 | Azure Storage (logs) | st-aml-logs-<env> | Standard_LRS | <region> | rg-aml-rd-<env> | <sub-id> | prod/stg/dev | Diagnostic log retention | Log Analytics | Retention: 30 days hot, 90 days cool.
5 | Azure Key Vault | kv-aml-rd-<env> | Standard | <region> | rg-aml-rd-<env> | <sub-id> | prod/stg/dev | Secrets & keys management | AML Workspace, ADO | Public access: Disabled. Soft delete: 90d. Purge protection: ON.
6 | Azure Container Registry | acr-aml-rd-<env> | Premium | <region> | rg-aml-rd-<env> | <sub-id> | prod/stg/dev | Docker image storage for ML environments | AML Workspace, ACA | Public access: Disabled. Admin user: OFF. Geo-replication: optional.
7 | Log Analytics Workspace | law-aml-rd-<env> | PerGB2018 | <region> | rg-aml-rd-<env> | <sub-id> | prod/stg/dev | Centralised log aggregation | All AML components | Retention: 30 days default (configurable). Diagnostic settings linked from all resources.
8 | Application Insights | appi-aml-rd-<env> | Standard | <region> | rg-aml-rd-<env> | <sub-id> | prod/stg/dev | ML endpoint telemetry | AML Workspace, Law | Sampling: Adaptive. Retention: 90 days.
9 | Virtual Network | vnet-aml-rd-<env> | N/A | <region> | rg-aml-net-<env> | <sub-id> | prod/stg/dev | AML spoke VNet | Hub VNet (peering) | Address space: 10.20.0.0/22. DNS: Private DNS Resolver inbound IP.
10 | Subnet - Compute | snet-aml-compute | N/A | <region> | rg-aml-net-<env> | <sub-id> | prod/stg/dev | AML Compute Instances & Clusters | vnet-aml-rd-<env> | CIDR: 10.20.0.0/24. NSG: nsg-aml-compute. Service endpoints: None (use private endpoints).
11 | Subnet - Endpoints | snet-aml-endpoints | N/A | <region> | rg-aml-net-<env> | <sub-id> | prod/stg/dev | Private Endpoints | vnet-aml-rd-<env> | CIDR: 10.20.1.0/24. Private endpoint network policies: Disabled.
12 | Subnet - Container Apps | snet-aca-runtime | N/A | <region> | rg-aml-net-<env> | <sub-id> | prod/stg/dev | Azure Container Apps runtime | vnet-aml-rd-<env> | CIDR: 10.20.2.0/24. Delegated to: Microsoft.App/environments.
13 | Subnet - DNS | snet-pe-dns | N/A | <region> | rg-aml-net-<env> | <sub-id> | prod/stg/dev | Private DNS Resolver inbound | vnet-aml-rd-<env> | CIDR: 10.20.3.0/28. Delegated to: Microsoft.Network/dnsResolvers.
14 | Compute Instance | ci-datasci-<user> | Standard_DS3_v2 | <region> | rg-aml-rd-<env> | <sub-id> | dev | Interactive data science development | AML Workspace, VNet | 4 vCPU, 14 GB RAM. Auto-stop: 18:00 + 30 min idle. No public IP.
15 | CPU Compute Cluster | cc-cpu-rd-<env> | Standard_D4s_v3 | <region> | rg-aml-rd-<env> | <sub-id> | prod/dev | Feature engineering, batch scoring | AML Workspace, VNet | Min: 0, Max: 4. Idle timeout: 120s. Scale-to-zero enforced.
16 | GPU Compute Cluster | cc-gpu-rd-<env> | Standard_NC6s_v3 | <region> | rg-aml-rd-<env> | <sub-id> | prod/dev | Model training (deep learning) | AML Workspace, VNet | Min: 0, Max: 2. Idle timeout: 120s. 1x NVIDIA V100 per node.
17 | Managed Online Endpoint | moe-<model>-<env> | Standard_DS2_v2 | <region> | rg-aml-rd-<env> | <sub-id> | prod/stg | Real-time model inference REST API | AML Workspace, ACR | Min: 1, Max: 3. Auth: Key. Public access: Disabled. Traffic: blue/green.
18 | Batch Endpoint | batch-<model>-<env> | CPU Cluster | <region> | rg-aml-rd-<env> | <sub-id> | prod | Batch inference (large volume) | AML Workspace, CPU Cluster | Mini-batch: 100. Retry: 3. Output: st-aml-data-<env>/batch-outputs/.
19 | Azure Container Apps Env | cae-aml-rd-<env> | Consumption | <region> | rg-aml-rd-<env> | <sub-id> | prod/dev | Container Apps hosting environment | VNet, ACR | VNet integrated. Internal ingress only.
20 | Azure Container App | ca-model-ui-<env> | Consumption | <region> | rg-aml-rd-<env> | <sub-id> | prod/dev | Model web UI / API gateway | cae-aml-rd-<env> | Image from ACR. Ingress: internal. Min replicas: 0. Max: 3.
21 | Private DNS Zone (AML) | privatelink.api.azureml.ms | N/A | Global | rg-aml-dns | <sub-id> | all | DNS for AML private endpoints | Hub + Spoke VNets | A records auto-created by PE. VNet link: Hub + AML spoke.
22 | Private DNS Zone (Blob) | privatelink.blob.core.windows.net | N/A | Global | rg-aml-dns | <sub-id> | all | DNS for Storage blob endpoints | Hub + Spoke VNets | A records auto-created by PE.
23 | Private DNS Zone (KV) | privatelink.vaultcore.azure.net | N/A | Global | rg-aml-dns | <sub-id> | all | DNS for Key Vault endpoint | Hub + Spoke VNets | A records auto-created by PE.
24 | Private DNS Zone (ACR) | privatelink.azurecr.io | N/A | Global | rg-aml-dns | <sub-id> | all | DNS for Container Registry endpoint | Hub + Spoke VNets | A records auto-created by PE.
25 | Private DNS Resolver | pdnsr-hub-<env> | Standard | <region> | rg-hub-net | <sub-id> | all | Hybrid DNS resolution (on-prem to Azure) | Hub VNet | Inbound: 10.20.3.4. Forwarding ruleset: privatelink.* to Azure DNS (168.63.129.16).
26 | VNet Peering (Spoke-Hub) | peer-aml-to-hub | N/A | <region> | rg-aml-net-<env> | <sub-id> | all | Connectivity spoke to hub | Hub VNet | Allow gateway transit: ON. Use remote gateways: ON. Allow forwarded traffic: ON.
27 | Azure DevOps Project | aml-workbench-rd | N/A | N/A | N/A | Customer ADO Org | all | CI/CD for AML model lifecycle | Customer ADO Org | Service connection: sp-aml-devops. Environments: dev, staging, production.
28 | Service Principal | sp-aml-devops | N/A | <region> | N/A | <sub-id> | all | ADO to Azure authentication | ADO, AML Workspace | Roles: AzureML Data Scientist + RG Contributor. Secret rotation: 12 months.

## Network
1. Virtual Network Design
VNet / Subnet | CIDR | Region | Resource Group | Purpose | NSG | Route Table | Notes
Hub VNet (existing) | Customer-defined | <region> | rg-hub-net | Central hub for spoke connectivity | nsg-hub | rt-hub | Managed by Customer network team. AML peered to hub.
vnet-aml-rd-<env> | 10.20.0.0/22 | <region> | rg-aml-net-<env> | AML workbench spoke VNet | N/A (per subnet) | rt-aml-default | DNS: Private DNS Resolver inbound IP (10.20.3.4)
snet-aml-compute | 10.20.0.0/24 | <region> | rg-aml-net-<env> | Compute Instances and Clusters | nsg-aml-compute | rt-aml-default | No public IP. All egress via Firewall.
snet-aml-endpoints | 10.20.1.0/24 | <region> | rg-aml-net-<env> | Private Endpoints | nsg-aml-pe | rt-aml-default | PE network policies: Disabled.
snet-aca-runtime | 10.20.2.0/24 | <region> | rg-aml-net-<env> | Azure Container Apps runtime | nsg-aca | rt-aml-default | Delegated: Microsoft.App/environments
snet-pe-dns | 10.20.3.0/28 | <region> | rg-aml-net-<env> | Private DNS Resolver inbound | nsg-dns | rt-aml-default | Delegated: Microsoft.Network/dnsResolvers
2. NSG Rules - snet-aml-compute
Priority | Name | Direction | Source | Destination | Port | Protocol | Action
100 | Allow-AML-BatchNodeMgmt | Inbound | BatchNodeManagement | * | 29876-29877 | TCP | Allow
110 | Allow-AML-Service | Inbound | AzureMachineLearning | * | 44224 | TCP | Allow
120 | Allow-HTTPS-Outbound | Outbound | * | Internet | 443 | TCP | Allow (via Firewall)
130 | Allow-Storage-Outbound | Outbound | * | Storage | 443 | TCP | Allow
140 | Allow-AzureAD-Outbound | Outbound | * | AzureActiveDirectory | 443 | TCP | Allow
150 | Allow-Monitor-Outbound | Outbound | * | AzureMonitor | 443 | TCP | Allow
4000 | Deny-All-Inbound | Inbound | * | * | * | * | Deny
4001 | Deny-All-Internet-Outbound | Outbound | * | Internet | * | * | Deny
3. Private Endpoints
Service | PE Name | Sub-resource | Private IP (example) | Private DNS Zone | DNS A Record | VNet Link | Status
Azure ML Workspace | pe-aml-workspace | amlworkspace | 10.20.1.4 | privatelink.api.azureml.ms | aml-rd-<env>.api.azureml.ms | Hub + AML | Deployed
Azure ML Notebooks | pe-aml-notebooks | notebooks | 10.20.1.5 | privatelink.notebooks.azure.net | aml-rd-<env>.notebooks.azure.net | Hub + AML | Deployed
Storage (default blob) | pe-st-default-blob | blob | 10.20.1.6 | privatelink.blob.core.windows.net | st-aml-default-<env>.blob.core.windows.net | Hub + AML | Deployed
Storage (data blob) | pe-st-data-blob | blob | 10.20.1.7 | privatelink.blob.core.windows.net | st-aml-data-<env>.blob.core.windows.net | Hub + AML | Deployed
Storage (default file) | pe-st-default-file | file | 10.20.1.8 | privatelink.file.core.windows.net | st-aml-default-<env>.file.core.windows.net | Hub + AML | Deployed
Key Vault | pe-kv-aml | vault | 10.20.1.9 | privatelink.vaultcore.azure.net | kv-aml-rd-<env>.vaultcore.azure.net | Hub + AML | Deployed
Container Registry | pe-acr-aml | registry | 10.20.1.10 | privatelink.azurecr.io | acr-aml-rd-<env>.azurecr.io | Hub + AML | Deployed
Managed Online Endpoint | pe-moe-<model> | amlworkspace | 10.20.1.11 | privatelink.api.azureml.ms | <model>-<env>.api.azureml.ms | Hub + AML | Per model
4. Site-to-Site VPN Configuration
Configuration Item | Value
Gateway Type | VPN Gateway (Route-based)
SKU | VpnGw2 (or existing Customer hub SKU)
Protocol | IKEv2
Tunnel Mode | Active-Passive (2 tunnels for resilience)
BGP | Enabled - ASN: Customer-defined
On-prem CIDR advertised | Customer on-premises network range(s)
Azure CIDR advertised to on-prem | 10.20.0.0/22 (AML spoke), Hub VNet CIDR
Shared Key | Stored in Key Vault (kv-hub-<env>)

## Security
1. RBAC Assignments
Principal | Principal Type | Azure RBAC Role | Scope | Environment | Justification | Notes
AzureML-DataScientist-<env> | Entra ID Group | AzureML Data Scientist | AML Workspace | prod/stg/dev | Core data scientist access for experiments, compute, models | JIT not required - standard role
AzureML-DataScientist-<env> | Entra ID Group | Storage Blob Data Contributor | st-aml-data-<env> | prod/stg/dev | Read/write access to R&D datasets | Scoped to data storage only
sp-aml-devops | Service Principal | AzureML Data Scientist | AML Workspace | prod/stg | ADO pipeline model training and deployment | Secret rotation: 12 months
sp-aml-devops | Service Principal | Contributor | rg-aml-rd-<env> | prod/stg | ADO pipeline infrastructure deployment | Scoped to AML RG only
aml-rd-<env> (System MI) | Managed Identity | Storage Blob Data Contributor | st-aml-default-<env>, st-aml-data-<env> | all | AML Workspace access to storage | No credential management required
aml-rd-<env> (System MI) | Managed Identity | AcrPull | acr-aml-rd-<env> | all | Pull Docker images for compute environments | Premium SKU required
aml-rd-<env> (System MI) | Managed Identity | Key Vault Secrets User | kv-aml-rd-<env> | all | Read workspace secrets | Get + List only
Rackspace-AML-<env> | Entra ID Group (JIT) | Contributor (time-limited) | rg-aml-rd-<env> | dev | Delivery team access during engagement | PIM JIT - 8 hour max sessions. Auto-expire post-delivery.
AzureML-Viewer-<env> | Entra ID Group | Reader | rg-aml-rd-<env> | prod | Read-only for management reporting | No modify permissions
2. Azure Firewall Rules (Hub Firewall - AML Traffic)
Rule Collection | Rule Name | Rule Type | Direction | Source | Destination | Action
RC-AML-Allow-Outbound | Allow-PyPI | Application | Outbound | AML Compute (10.20.0.0/24) | *.pypi.org, *.anaconda.com, *.conda.io, files.pythonhosted.org | Allow
RC-AML-Allow-Outbound | Allow-Azure-Services | Application | Outbound | AML Compute (10.20.0.0/24) | *.microsoft.com, *.azure.com, *.azureml.ms, *.azureedge.net | Allow
RC-AML-Allow-Outbound | Allow-Ubuntu-Repos | Application | Outbound | AML Compute (10.20.0.0/24) | *.ubuntu.com, *.docker.io, registry-1.docker.io | Allow
RC-AML-Allow-Outbound | Allow-GitHub | Application | Outbound | AML Compute (10.20.0.0/24) | *.github.com, *.githubusercontent.com | Allow
RC-AML-Allow-Network | Allow-Monitor | Network | Outbound | AML Compute (10.20.0.0/24) | AzureMonitor:443 | Allow
RC-AML-Allow-Network | Allow-AAD | Network | Outbound | AML Compute (10.20.0.0/24) | AzureActiveDirectory:443 | Allow
RC-AML-Allow-Network | Allow-Storage-SvcTag | Network | Outbound | AML Compute (10.20.0.0/24) | Storage:<region>:443 | Allow
RC-AML-Deny-Default | Deny-All-Internet | Network | Outbound | AML Compute (10.20.0.0/24) | Internet:* | Deny
3. Key Vault Configuration
Configuration Item | Value
Name | kv-aml-rd-<env>
SKU | Standard (Premium with HSM for CMK)
Public Network Access | Disabled - Private Endpoint only
Soft Delete | Enabled - 90 day retention
Purge Protection | Enabled (cannot be disabled once set)
RBAC Model | Azure RBAC (not Vault Access Policies)
Secrets Stored | Storage account keys, ACR token, ADO SP secret, external API keys
Key Rotation | Automatic rotation policy: 90 days, notify 14 days before expiry
Diagnostic Logs | All operations to law-aml-rd-<env>
Network ACL | Allow from snet-aml-endpoints (via PE) only
4. Azure Policies
Policy ID | Policy Name | Mode | Scope | Effect | Rationale | Customer-owned?
POL-001 | Require tags on resource groups (Environment, Project, CostCenter) | All | Management Group | Deny | Governance and cost tracking | Yes (ALZ)
POL-002 | Storage accounts must disable public blob access | Indexed | AML RG | Audit + Deny | Data protection - no public data exposure | Yes (ALZ)
POL-003 | Key Vault must have soft delete enabled | Indexed | AML RG | Audit | Prevent accidental secret deletion | Rackspace deploys
POL-004 | Key Vault must have purge protection enabled | Indexed | AML RG | Audit | Prevent permanent deletion | Rackspace deploys
POL-005 | AML Workspace public network access must be disabled | Indexed | AML RG | Audit + Deny | Network isolation enforcement | Rackspace deploys
POL-006 | Deny creation of public IP addresses | Indexed | AML RG | Deny | No public exposure from AML resources | Rackspace deploys
POL-007 | Allowed locations | Indexed | AML Subscription | Deny | Data residency control | Yes (ALZ)

## Compute
1. Compute Instance Configuration
Parameter | Value (User 1) | Value (User 2) | Notes
Name | ci-datasci-user1 | ci-datasci-user2 | Max 1 per user for cost control
VM Size | Standard_DS3_v2 | Standard_DS3_v2 | 4 vCPU, 14 GB RAM, 28 GB temp disk
OS | Ubuntu 20.04 LTS | Ubuntu 20.04 LTS | AML-managed image
Public IP | None | None | Accessed via AML Studio (private)
Auto-stop - Idle | 30 minutes | 30 minutes | Prevents overnight charges
Auto-stop - Scheduled | 18:00 (Customer TZ) | 18:00 (Customer TZ) | Configurable per user
Assigned User | datasci-user1@flora.com | datasci-user2@flora.com | Single-user assignment enforced
Managed Identity | System-assigned | System-assigned | Access to storage and KV without credentials
Pre-installed Packages | Python 3.10, azureml-sdk, mlflow, scikit-learn, pandas, numpy, pytorch | Same as User 1 | Conda environment: flora-rd-base
R Support | R 4.3+ kernel available | R 4.3+ kernel available | Via Jupyter R kernel
Storage Mount | Azure Files share (private PE) | Azure Files share (private PE) | /home/<user> persisted across restarts
SSH Access | Disabled (use AML Studio terminal) | Disabled | No direct SSH exposure
Subnet | snet-aml-compute | snet-aml-compute | 10.20.0.0/24
2. CPU Compute Cluster
Parameter | Value | Notes
Name | cc-cpu-rd-<env> | Environment suffix: prod / dev
VM Size | Standard_D4s_v3 | 4 vCPU, 16 GB RAM, 32 GB temp SSD
OS Disk | Premium SSD | 128 GB
Min Nodes | 0 | Scale to zero when idle (cost saving)
Max Nodes | 4 | Autoscale; adjust per workload demand
Idle Timeout | 120 seconds | Low to ensure rapid scale-down
Priority | Dedicated | Switch to Low-Priority for further cost saving (risk: eviction)
Subnet | snet-aml-compute (10.20.0.0/24) | No public IP
Use Cases | Feature engineering, batch scoring, data preprocessing, AML pipeline steps
Managed Identity | System-assigned Managed Identity of cluster | Access to storage and ACR
3. GPU Compute Cluster
Parameter | Value | Notes
Name | cc-gpu-rd-<env>
VM Size | Standard_NC6s_v3 | 6 vCPU, 112 GB RAM, 1x NVIDIA Tesla V100 (16 GB VRAM)
Min Nodes | 0 | Scale to zero - GPU is intermittent use only
Max Nodes | 2 | Sufficient for 2 concurrent training jobs
Idle Timeout | 120 seconds
Priority | Dedicated (Spot optional for dev) | Spot pricing saves ~80% but risk of eviction
CUDA Version | CUDA 11.x (via AML curated environment) | Custom CUDA via Docker in ACR
Subnet | snet-aml-compute (10.20.0.0/24) | No public IP
Quota Pre-requisite | Standard_NCSv3Family - Customer must request quota | Default quota is 0 in most regions
Use Cases | PyTorch / TensorFlow training, fine-tuning pre-trained models
Fallback SKU | Standard_NV6 or Standard_NC6 (non-v3) | If NCSv3 quota unavailable

## Storage
1. Storage Account Summary
Storage Account | Tier/Replication | Containers / File Shares | Access Tier | Encryption | Lifecycle Policy | Notes
st-aml-default-<env> | Standard_LRS | aml-default (AML managed), azureml-filestore (File Share), azureml-metrics | Hot | Microsoft-managed keys (MMK) | Archive blobs >90 days; delete after 365 days | Default AML workspace storage. Soft delete: 14 days.
st-aml-data-<env> | Standard_LRS | raw-input/, validated/, batch-outputs/, references/ | Hot / Cool (tiering rule) | MMK (CMK upgrade path) | Move to Cool after 30 days, archive after 90 days | R&D dataset storage. HNS (ADLS Gen2) enabled.
st-aml-logs-<env> | Standard_LRS | diagnostic-logs/, run-logs/, audit-logs/ | Cool | MMK | Delete after 90 days | Log and audit storage. No compute or model access.
2. Azure ML Datastores Registration
Datastore Name | Type | Storage Account | Container / Path | Credentials | Default? | Purpose
workspaceblobstore | Azure Blob Storage | st-aml-default-<env> | azureml-blobstore-{ws-guid}/ | Workspace Managed Identity | Yes | AML default - run outputs, snapshots, checkpoints
workspacefilestore | Azure File Share | st-aml-default-<env> | azureml-filestore-{ws-guid}/ | Workspace Managed Identity | No | Compute Instance home directory persistent storage
flora-data-raw | Azure Blob Storage (ADLS) | st-aml-data-<env> | raw-input/ | Workspace Managed Identity | No | Raw R&D input datasets
flora-data-validated | Azure Blob Storage (ADLS) | st-aml-data-<env> | validated/ | Workspace Managed Identity | No | Validated/curated datasets for training
flora-batch-outputs | Azure Blob Storage | st-aml-data-<env> | batch-outputs/ | Workspace Managed Identity | No | Batch inference output results

## MLOps
1. Azure DevOps Project Configuration
Configuration Item | Value
ADO Organisation | Customer-provided (Flora Food ADO tenant)
Project Name | aml-workbench-rd
Visibility | Private
Repositories | aml-workbench-rd (main repo - Git)
Service Connection | sc-aml-azure-<env> (Service Principal: sp-aml-devops)
Variable Groups | vg-aml-dev, vg-aml-staging, vg-aml-prod (KV linked - no secrets in ADO)
Environments | dev (auto-deploy), staging (auto-deploy), production (manual approval required)
Branch Strategy | main (production), staging (staging deploy), dev (development)
Agent Pool | Azure-hosted: ubuntu-latest (or Customer self-hosted if required)
2. CI/CD Pipeline Definitions
Pipeline | File Path | Trigger | Agent | Steps | Target Environment | Approval Gate | Est. Runtime
ci-model-train | .azuredevops/ci-model-train.yml | PR to main / push to dev branch | ubuntu-latest | 1.Lint+Unit Test 2.az ml job create (train) 3.Register model in Registry | dev | None | 15-45 min (GPU training)
cd-model-deploy-staging | .azuredevops/cd-staging.yml | Model version tagged 'staging' in Registry | ubuntu-latest | 1.Build Docker image 2.az acr build 3.az ml online-deployment create 4.Integration test 5.Tag endpoint 'staging' | staging | None (auto) | 10-20 min
cd-model-deploy-prod | .azuredevops/cd-prod.yml | Manual trigger / approved PR | ubuntu-latest | 1.Blue-green shift 10% traffic 2.Smoke test 3.Shift 100% 4.Tag 'production' 5.Notify | production | Yes - Customer SME approval | 10-15 min
ci-infra | .azuredevops/ci-infra.yml | Changes to infra/ folder | ubuntu-latest | 1.Bicep lint 2.az deployment what-if 3.Manual approval 4.az deployment create | all | Yes - Architect approval | 20-30 min
batch-score | .azuredevops/batch-score.yml | Scheduled (weekly) or manual trigger | ubuntu-latest | 1.Get latest production model 2.az ml batch-endpoint invoke 3.Monitor job 4.Copy results | production | None | Job-dependent
env-update | .azuredevops/env-update.yml | Changes to environments/ folder | ubuntu-latest | 1.az ml environment create 2.Test build 3.Push to ACR 4.Validate | dev | None | 15-25 min
3. ML Model Lifecycle Stages
Stage | Model Registry Tag | Trigger | Validation Required | Endpoint | Promotion Criteria | Rollback Mechanism | Owner
Development | dev | ci-model-train pipeline completes | Unit tests pass, metrics logged | None (training only) | Metrics exceed baseline threshold | Re-run training job | Data Scientist
Staging | staging | SME reviews dev model; manually promotes | Integration tests against test dataset | Staging Online Endpoint | Integration tests pass, no data drift | Redeploy previous staging version | MLOps Engineer
Production | production | Customer SME approves staging deployment | Smoke test on production endpoint | Production Online Endpoint (blue/green) | Smoke test pass, P99 latency <500ms | Traffic shift back to previous blue deployment | Customer SME + MLOps
Archived | archived | Superseded by newer production version | None | N/A | N/A | Restore version from Model Registry | Customer IT

## Monitoring
1. Log Analytics & Diagnostic Settings
Resource | Diagnostic Setting Name | Log Categories Enabled | Metrics Enabled | Destination | Retention | Notes
Azure ML Workspace | diag-aml-workspace | AmlComputeClusterEvent, AmlRunStatusChangedEvent, AmlComputeClusterNodeEvent, ModelsChangeEvent, DeploymentEvent | AllMetrics | law-aml-rd-<env> | 30 days | Covers training, deployment, and model events
Azure Key Vault | diag-kv-aml | AuditEvent, AzurePolicyEvaluationDetails | AllMetrics | law-aml-rd-<env> | 90 days | All secret access logged for security audit
Azure Storage (all accounts) | diag-st-aml | StorageRead, StorageWrite, StorageDelete | Transaction, Capacity | law-aml-rd-<env> | 30 days | Data access auditing
Azure Container Registry | diag-acr-aml | ContainerRegistryLoginEvents, ContainerRegistryRepositoryEvents | AllMetrics | law-aml-rd-<env> | 30 days | Image push/pull audit trail
Azure Firewall (Hub) | diag-fw-hub | AzureFirewallApplicationRule, AzureFirewallNetworkRule, AzureFirewallDnsProxy | AllMetrics | law-aml-rd-<env> | 30 days | Network traffic audit for AML workloads
Application Insights | N/A (native collection) | Traces, Exceptions, Requests, Dependencies | Availability | law-aml-rd-<env> | 90 days | ML endpoint telemetry
2. Azure Monitor Alerts
Alert Name | Resource | Signal | Threshold | Severity | Action Group | Evaluation Frequency
GPU-Cluster-HighUtil | cc-gpu-rd-<env> | GPU Utilisation % | > 80% for 10 min | Sev 2 - Warning | ag-aml-team | 5 min
Endpoint-ErrorRate | moe-<model>-prod | Request Failed Count | > 5% error rate over 5 min | Sev 1 - Critical | ag-aml-team | 1 min
Endpoint-Latency-P99 | moe-<model>-prod | P99 Latency | > 2000ms | Sev 2 - Warning | ag-aml-team | 1 min
Storage-Capacity | st-aml-data-<env> | Used Capacity | > 80% of provisioned | Sev 2 - Warning | ag-aml-team | 1 hour
KV-Access-Denied | kv-aml-rd-<env> | Audit - SecretGet failed | Any failure | Sev 1 - Critical | ag-aml-security | 1 min
AML-Job-Failed | aml-rd-<env> | AmlRunStatusChangedEvent (status=Failed) | Any failure | Sev 2 - Warning | ag-aml-team | 5 min
Firewall-Deny-Spike | Azure Firewall (Hub) | AzureFirewallNetworkRule - Action=Deny | > 50 denies/min | Sev 2 - Warning | ag-aml-security | 5 min
Cost-Budget-Alert | rg-aml-rd-<env> | Actual Cost | > 80% of monthly budget | Sev 3 - Informational | ag-aml-team | Daily
3. Data Drift Monitoring
Monitor Name | Dataset (Baseline) | Dataset (Target) | Features Monitored | Frequency | Drift Threshold | Alert on Drift?
drift-monitor-flora-model-a | flora-train-baseline-v1 | flora-live-scoring-data | All input features (auto-detect) | Weekly | Normalized Wasserstein Distance > 0.2 | Yes - Sev 2 alert
drift-monitor-flora-model-b | flora-train-baseline-v1 | flora-live-scoring-data | All input features | Weekly | Normalized Wasserstein Distance > 0.2 | Yes - Sev 2 alert

## Naming
Azure Resource Naming Convention - Flora AML Workbench
Format: <resource-type>-<workload>-<env>[-<instance>] ¦ env: prod / stg / dev ¦ All lowercase, hyphens only, max 63 chars (storage: 24)
Resource Type | Abbreviation | Example Name | Max Length | Constraints | Notes
Resource Group | rg- | rg-aml-rd-prod | 90 | Letters, digits, underscores, periods, hyphens | One per environment
Azure ML Workspace | aml- | aml-rd-prod | 260 | Letters, digits, hyphens. Start with letter | Globally unique within RG
Storage Account | st | stamldefaultprod | 3-24 | Lowercase letters and digits only | No hyphens! Globally unique
Key Vault | kv- | kv-aml-rd-prod | 3-24 | Alphanumeric and hyphens. Start with letter | Globally unique
Container Registry | acr | acr-aml-rd-prod | 5-50 | Alphanumeric only (no hyphens in login server) | Globally unique
Log Analytics Workspace | law- | law-aml-rd-prod | 63 | Letters, digits, hyphens | Unique per RG
Application Insights | appi- | appi-aml-rd-prod | 255 | Letters, digits, hyphens, periods
Virtual Network | vnet- | vnet-aml-rd-prod | 64 | Letters, digits, underscores, periods, hyphens
Subnet | snet- | snet-aml-compute | 80 | Letters, digits, underscores, periods, hyphens
Network Security Group | nsg- | nsg-aml-compute | 80 | Letters, digits, underscores, periods, hyphens
Route Table | rt- | rt-aml-default | 80 | Letters, digits, underscores, periods, hyphens
Private Endpoint | pe- | pe-aml-workspace | 80 |  | <resource-type>-<service>
Private DNS Zone | (FQDN) | privatelink.api.azureml.ms | 253 | Valid DNS zone name | Pre-defined by Azure
Compute Instance | ci- | ci-datasci-user1 | 24 | Letters and digits only (no hyphens) | Per-user
CPU Compute Cluster | cc-cpu- | cc-cpu-rd-prod | 16 | Letters and digits only
GPU Compute Cluster | cc-gpu- | cc-gpu-rd-prod | 16 | Letters and digits only
Managed Online Endpoint | moe- | moe-modelA-prod | 32 | Lowercase letters and digits, hyphens | Globally unique within region
Batch Endpoint | batch- | batch-modelA-prod | 32 | Lowercase letters and digits, hyphens
Container Apps Environment | cae- | cae-aml-rd-prod | 60 | Lowercase letters, digits, hyphens
Container App | ca- | ca-model-ui-prod | 32 | Lowercase letters, digits, hyphens
Service Principal | sp- | sp-aml-devops | 120 |  | Descriptive; include tenant prefix
ADO Project | (human readable) | aml-workbench-rd | 64 |  | Kebab-case preferred
ADO Variable Group | vg- | vg-aml-prod
ADO Service Connection | sc- | sc-aml-azure-prod
Azure Monitor Alert | alert- | alert-gpu-util-prod
Action Group | ag- | ag-aml-team

## Milestones
Delivery Milestones, Acceptance Criteria & RACI
Milestone | Name | Duration | Fee (EUR) | Key Activities | Deliverables | Acceptance Criteria | Status
MS1 | Project Kickoff & Mobilisation | ~1 week | 3,000 | Kickoff meeting, access provisioning request, review ALZ design, confirm architecture, agree RACI | Kickoff deck, access checklist, architecture confirmation sign-off | 1. Rackspace granted access to Azure subscription and ADO org 2. Architecture confirmed by Customer 3. RACI agreed | Not Started
MS2 | Platform Discovery & Design | ~2 weeks | 4,000 | ALZ integration review, deploy AML Workspace, configure compute, storage, KV, private endpoints, VNet | Deployed AML Workspace, Compute Instances, CPU/GPU clusters, Storage accounts, Key Vault, Private endpoints | 1. AML Workspace deployed and accessible 2. Compute Instances operational 3. CPU/GPU clusters deployable 4. Private endpoints configured 5. AML Studio accessible from on-premises via VPN | Not Started
MS3 | MLOps, Endpoint & Observability | ~3 weeks | 7,000 | MLflow integration, Model Registry setup, Online Endpoint deployment, Batch Endpoint, ADO pipelines, monitoring | MLflow tracking working, Model Registry, Online Endpoint, Batch Endpoint, ADO CI/CD pipelines, Monitor dashboard | 1. MLflow experiments logged 2. Model registered in Registry 3. Online Endpoint deployed and accessible 4. ADO pipeline executes training and deployment 5. Monitoring alerts active | Not Started
MS4 | Project Closure | ~1 week | 6,000 | End-to-end validation, documentation finalisation, 2x knowledge transfer sessions (2h each), formal handover | Architecture design document, LLD, operational runbook, knowledge transfer materials, handover sign-off | 1. E2E pipeline executed successfully 2. At least 1 model in production endpoint 3. All documentation delivered 4. Knowledge transfer sessions completed 5. Customer sign-off received | Not Started
RACI Matrix
Activity | Rackspace Arch | Rackspace PM | Customer IT | Customer SME | Customer Security | Customer Finance | ADO Team
Architecture Design | R,A | C | C | I | C | I | I
Azure Subscription Access | I | C | R,A | I | C | I | I
Network / VPN Configuration | C | I | R,A | I | R | I | I
AML Workspace Deployment | R,A | I | C | I | C | I | I
Compute Configuration | R,A | I | I | C | I | I | I
MLflow / Registry Setup | R,A | I | I | C | I | I | I
ADO Pipeline Setup | R,A | I | I | C | I | I | C
RBAC / IAM Policy | C | I | R,A | I | R | I | I
Security Policy Enforcement | I | I | C | I | R,A | I | I
Testing / Validation | R | C | C | R,A | C | I | I
Documentation | R,A | C | I | C | I | I | I
Knowledge Transfer | R,A | I | C | R | I | I | I
Cost Management | I | C | C | I | I | R,A | I
Post-Delivery Operations | I | I | R,A | R,A | R | R | C
Legend: R = Responsible A = Accountable C = Consulted I = Informed

## Risks
ID | Risk Description | Category | Likelihood | Impact | Risk Score | Mitigation | Owner | Status
R-01 | Delayed access to Customer Azure subscription or ADO organisation at project start | Access | Medium | High | High | Confirm access requirements in MS1 kickoff. Define escalation path and SLA for access provisioning. | Customer IT | Open
R-02 | ALZ network policies block private endpoint DNS resolution (on-premises to Azure) | Network | Medium | High | High | DNS architecture reviewed in MS1. Private DNS Resolver design pre-validated against ALZ network team. | Rackspace + Customer IT | Open
R-03 | GPU quota (Standard_NC6s_v3) not available in target Azure region | Compute | Low | High | Medium | Customer to submit GPU quota request pre-MS2. Fallback SKU (Standard_NV6) documented. | Customer IT | Open
R-04 | Customer RBAC model not defined at project start, blocking workspace access configuration | Security | Medium | Medium | Medium | Rackspace provides RBAC matrix template (in this LLD). Customer SME to approve within MS1. | Customer Security | Open
R-05 | Scope creep: request to build data engineering pipelines or Databricks integration | Scope | Medium | Medium | Medium | SOW Section 3 clearly documents out-of-scope items. Change Control Procedure to be invoked for any additions. | Rackspace PM | Open
R-06 | Data sensitivity requirement for Customer-managed encryption keys (CMK) discovered post-design | Security | Low | Medium | Low | CMK upgrade path documented in DDD. Additional effort required via Change Request if CMK mandated. | Customer Security | Open
R-07 | On-premises VPN tunnel instability affecting data scientist access to AML Studio | Network | Low | Medium | Low | Dual-tunnel active-passive VPN. Azure Bastion documented as fallback access path. | Customer IT | Open
R-08 | Azure ML service outage affecting training or serving during critical delivery window | Platform | Low | Low | Low | Monitor Azure Service Health. AML Managed Endpoints have built-in SLAs. Batch workloads can be re-queued. | Rackspace | Open
R-09 | Data scientist team unavailable for knowledge transfer sessions | Resource | Low | Medium | Low | Minimum 2 KT sessions (2h each) scheduled in MS4. Materials recorded and documented for async consumption. | Customer SME | Open

## Cost Estimate
Indicative Monthly Azure Consumption Cost Estimate - Flora AML Workbench (R&D Scale)
Note: These are estimates only. Actual costs depend on usage patterns, negotiated discounts, and Azure pricing at time of deployment. Verify in Azure Pricing Calculator.
Component | Resource | SKU | Qty | Est. Hours/Month | Unit Price (USD) | Est. Monthly Cost (USD)
Compute Instance | ci-datasci (x2) | Standard_DS3_v2 | 2 | 160 hrs (8h/day x 20 days) | $0.23/hr | ~$74
CPU Compute Cluster | cc-cpu-rd | Standard_D4s_v3 | 0-4 nodes | Variable (~40 hrs) | $0.19/hr/node | ~$30
GPU Compute Cluster | cc-gpu-rd | Standard_NC6s_v3 | 0-2 nodes | Intermittent (~20 hrs) | $3.06/hr/node | ~$122
Online Endpoint (Deployment) | moe-modelA-prod (DS2_v2 x1) | Standard_DS2_v2 | 1 | 720 hrs (always-on) | $0.096/hr | ~$69
Storage - Default | st-aml-default | Standard_LRS | 50 GB avg | N/A | $0.018/GB | ~$1
Storage - Data | st-aml-data | Standard_LRS | 100 GB avg | N/A | $0.018/GB | ~$2
Key Vault | kv-aml-rd | Standard | 1 | 10k operations | $0.03/10k ops | ~$0.03
Container Registry | acr-aml-rd | Premium | 1 | 1 unit | $0.667/day | ~$20
Log Analytics | law-aml-rd | Pay-per-GB | ~5 GB/day ingestion | N/A | $2.76/GB | ~$414
Application Insights | appi-aml-rd | Standard | 1 GB/month | N/A | $2.30/GB | ~$2
Private DNS Zones | ~8 zones | N/A | 8 | N/A | $0.50/zone/month | ~$4
Private DNS Resolver | pdnsr-hub | Standard | 1 | 720 hrs | $0.07/hr | ~$50
Private Endpoints | ~8 endpoints | N/A | 8 | N/A | $0.01/hr each | ~$58
VNet Peering | AML spoke <-> Hub | N/A | 1 | Data transfer | ~$0.01/GB | Variable
Azure Firewall | (Hub - shared) | Premium | Pro-rated share | 720 hrs | ~$2.50/hr (shared) | ~$50 (share)
[5 empty] | TOTAL ESTIMATE | ~$896 / month
Log Analytics cost is significant. Consider configuring Basic Log tier for verbose diagnostic tables. Actual cost optimisation to be reviewed post-deployment.